## main
DOE G 413.3-19 STAFFING MODEL
GENERAL INFORMATION
name | name of individual completing this spreadsheet, e.g., FPD
review/purpose | type of review (e.g., IPT meeting, EIR, IPR, PPR,...) and purpose (e.g., support review, develop staffing plan,...)
date
version
program
project no. | xx-xx-xxxx
project name | sample project
comment
documentation used for this analysis | provide list of documentation (including title, date, and document number) for all factors (e.g., PDS, PEP, staffing plan,...)
PROJECT CHARACTERISTICS
FACTORS | PT | HC | TR | IR | PC | PE | RI | EI | PU | CT
project characteristics | construction | HC1 | Medium | PP | High | DOE M&O | Medium | Low | No | Incentive (cost-reimbursement)
factor values | 0.025 | High |  | Low | 0.2 | 0.2 | 0.05 | 0 | 0 | 0.1
PROJECT INFORMATION BY FY
FY | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
PP | CD-0 | CD-1 | CD-1 | CD-2 | CD-2 | CD-3 | CD-3 | CD-3 | CD-3 | CD-3
no. months PP for FY | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
PV planned value ($M) | 20 | 50 | 75 | 100 | 100 | 300 | 300 | 250 | 250 | 150
PF productivity factor ($M/FTE/FY) | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10
factor values, total | 2.575 | 1.675 | 1.675 | 1.075 | 1.075 | 0.575 | 0.575 | 0.575 | 0.575 | 0.575
PLANNED PROJECT STAFFING (FTE) BY FY
FY | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
PP | CD-0 | CD-1 | CD-1 | CD-2 | CD-2 | CD-3 | CD-3 | CD-3 | CD-3 | CD-3
contracting, subcontracting, and property management | 1 | 1 | 1 | 1 | 1 | 9 | 9 | 7 | 7 | 4
program and project planning, control and management | 2 | 4 | 4 | 6 | 6 | 9 | 9 | 8 | 8 | 5
science, engineering, and design support | 2 | 4 | 4 | 6 | 6 | 8 | 8 | 8 | 6 | 4
construction oversight and management |  |  |  | 1 | 1 | 4 | 4 | 4 | 4 | 3
quality assurance |  |  | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 1
environment, safety, and health | 2 | 2 | 3 | 5 | 5 | 6 | 6 | 6 | 6 | 4
finance and administration | 0.5 | 0.5 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 2
safeguards and security | 0.5 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
operations oversight |  |  |  | 2 | 2 | 4 | 4 | 4 | 4 | 3
public affairs and stakeholder relations | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
total | 8.5 | 13 | 15.5 | 26.5 | 26.5 | 46.5 | 46.5 | 43.5 | 41.5 | 27.5
FUNCTIONAL AREA PERCENTAGES BY FY
FY | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
PP | CD-0 | CD-1 | CD-1 | CD-2 | CD-2 | CD-3 | CD-3 | CD-3 | CD-3 | CD-3
contracting, subcontracting, and property management | 15% | 5% | 5% | 5% | 5% | 20% | 20% | 20% | 20% | 20%
program and project planning, control and management | 25% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20% | 20%
science, engineering, and design support | 25% | 40% | 40% | 25% | 25% | 20% | 20% | 20% | 20% | 20%
construction oversight and management | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5%
quality assurance | 0% | 0% | 0% | 9% | 9% | 5% | 5% | 5% | 5% | 5%
environment, safety, and health | 20% | 20% | 20% | 20% | 20% | 10% | 10% | 10% | 10% | 10%
finance and administration | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5%
safeguards and security | 5% | 5% | 5% | 5% | 5% | 4% | 4% | 4% | 4% | 4%
operations oversight | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
public affairs and stakeholder relations | 5% | 5% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 1%
total | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
PROJECT STAFFING (MODEL) (FTE) BY FY
FY | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
PP | CD-0 | CD-1 | CD-1 | CD-2 | CD-2 | CD-3 | CD-3 | CD-3 | CD-3 | CD-3
contracting, subcontracting, and property management | 1.0725 | 0.66875 | 1.0031 | 1.0375 | 1.0375 | 9.45 | 9.45 | 7.875 | 7.875 | 4.725
program and project planning, control and management | 1.7875 | 2.675 | 4.0125 | 4.15 | 4.15 | 9.45 | 9.45 | 7.875 | 7.875 | 4.725
science, engineering, and design support | 1.7875 | 5.35 | 8.025 | 5.1875 | 5.1875 | 9.45 | 9.45 | 7.875 | 7.875 | 4.725
construction oversight and management | 0 | 0 | 0 | 0 | 0 | 2.3625 | 2.3625 | 1.9688 | 1.9688 | 1.1813
quality assurance | 0 | 0 | 0 | 1.8675 | 1.8675 | 2.3625 | 2.3625 | 1.9688 | 1.9688 | 1.1813
environment, safety, and health | 1.43 | 2.675 | 4.0125 | 4.15 | 4.15 | 4.725 | 4.725 | 3.9375 | 3.9375 | 2.3625
finance and administration | 0.3575 | 0.66875 | 1.0031 | 1.0375 | 1.0375 | 2.3625 | 2.3625 | 1.9688 | 1.9688 | 1.1813
safeguards and security | 0.3575 | 0.66875 | 1.0031 | 1.0375 | 1.0375 | 1.89 | 1.89 | 1.575 | 1.575 | 0.945
operations oversight | 0 | 0 | 0 | 2.075 | 2.075 | 4.725 | 4.725 | 3.9375 | 3.9375 | 2.3625
public affairs and stakeholder relations | 0.3575 | 0.66875 | 1.0031 | 0.2075 | 0.2075 | 0.4725 | 0.4725 | 0.39375 | 0.39375 | 0.23625
total | 7.15 | 13.375 | 20.0625 | 20.75 | 20.75 | 47.25 | 47.25 | 39.375 | 39.375 | 23.625
total +20% | 8.58 | 16.05 | 24.075 | 24.9 | 24.9 | 56.7 | 56.7 | 47.25 | 47.25 | 28.35
total -20% | 5.72 | 10.7 | 16.05 | 16.6 | 16.6 | 37.8 | 37.8 | 31.5 | 31.5 | 18.9
PROJECT STAFFING (DELTA: PLANNED - MODEL) (FTE) BY FY
FY | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
PP | CD-0 | CD-1 | CD-1 | CD-2 | CD-2 | CD-3 | CD-3 | CD-3 | CD-3 | CD-3
contracting, subcontracting, and property management | -0.0725 | 0.33125 | -0.003125 | -0.0375 | -0.0375 | -0.45 | -0.45 | -0.875 | -0.875 | -0.725
program and project planning, control and management | 0.2125 | 1.325 | -0.0125 | 1.85 | 1.85 | -0.45 | -0.45 | 0.125 | 0.125 | 0.275
science, engineering, and design support | 0.2125 | -1.35 | -4.025 | 0.8125 | 0.8125 | -1.45 | -1.45 | 0.125 | -1.875 | -0.725
construction oversight and management | 0 | 0 | 0 | 1 | 1 | 1.6375 | 1.6375 | 2.0312 | 2.0312 | 1.8187
quality assurance | 0 | 0 | 1 | 0.1325 | 0.1325 | -0.3625 | -0.3625 | 0.03125 | 0.03125 | -0.18125
environment, safety, and health | 0.57 | -0.675 | -1.0125 | 0.85 | 0.85 | 1.275 | 1.275 | 2.0625 | 2.0625 | 1.6375
finance and administration | 0.1425 | -0.16875 | -0.003125 | 0.9625 | 0.9625 | 0.6375 | 0.6375 | 1.0312 | 1.0312 | 0.81875
safeguards and security | 0.1425 | 0.33125 | -0.003125 | -0.0375 | -0.0375 | -0.89 | -0.89 | -0.575 | -0.575 | 0.055
operations oversight | 0 | 0 | 0 | -0.075 | -0.075 | -0.725 | -0.725 | 0.0625 | 0.0625 | 0.6375
public affairs and stakeholder relations | 0.1425 | -0.16875 | -0.50313 | 0.2925 | 0.2925 | 0.0275 | 0.0275 | 0.10625 | 0.10625 | 0.26375
total | 1.35 | -0.375 | -4.5625 | 5.75 | 5.75 | -0.75 | -0.75 | 4.125 | 2.125 | 3.875
PROJECT STAFFING (%: PLANNED/MODEL) BY FY
FY | 2016 | 2017 | 2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025
PP | CD-0 | CD-1 | CD-1 | CD-2 | CD-2 | CD-3 | CD-3 | CD-3 | CD-3 | CD-3
contracting, subcontracting, and property management | 93.24% | 149.5% | 99.69% | 96.39% | 96.39% | 95.24% | 95.24% | 88.89% | 88.89% | 84.66%
program and project planning, control and management | 111.9% | 149.5% | 99.69% | 144.6% | 144.6% | 95.24% | 95.24% | 101.6% | 101.6% | 105.8%
science, engineering, and design support | 111.9% | 74.77% | 49.84% | 115.7% | 115.7% | 84.66% | 84.66% | 101.6% | 76.19% | 84.66%
construction oversight and management | . | . | . | . | . | 169.3% | 169.3% | 203.2% | 203.2% | 254%
quality assurance | . | . | . | 107.1% | 107.1% | 84.66% | 84.66% | 101.6% | 101.6% | 84.66%
environment, safety, and health | 139.9% | 74.77% | 74.77% | 120.5% | 120.5% | 127% | 127% | 152.4% | 152.4% | 169.3%
finance and administration | 139.9% | 74.77% | 99.69% | 192.8% | 192.8% | 127% | 127% | 152.4% | 152.4% | 169.3%
safeguards and security | 139.9% | 149.5% | 99.69% | 96.39% | 96.39% | 52.91% | 52.91% | 63.49% | 63.49% | 105.8%
operations oversight | . | . | . | 96.39% | 96.39% | 84.66% | 84.66% | 101.6% | 101.6% | 127%
public affairs and stakeholder relations | 139.9% | 74.77% | 49.84% | 241% | 241% | 105.8% | 105.8% | 127% | 127% | 211.6%
total | 118.9% | 97.2% | 77.26% | 127.7% | 127.7% | 98.41% | 98.41% | 110.5% | 105.4% | 116.4%
chart label | FY2016, CD-0, 12 months | FY2017, CD-1, 12 months | FY2018, CD-1, 12 months | FY2019, CD-2, 12 months | FY2020, CD-2, 12 months | FY2021, CD-3, 12 months | FY2022, CD-3, 12 months | FY2023, CD-3, 12 months | FY2024, CD-3, 12 months | FY2025, CD-3, 12 months
project no./name | Project Staffing (Planned vs. Model) by Fiscal Year xx-xx-xxxx, sample project
Note on C15: ref.: DOE-STD-1027-92, Attachment 1.
Note on E15: ref.: DOE O 470.4B Chg 2, Appendix B, Section 1, Chapter II.
Note on F15: Auto generated based on HC, TR, and IR.
Note on K15: ref.: FAR Parts 16 and 17.6.
Note on A74: Bolded if delta is >=2.

## instructions
INSTRUCTIONS
• This tool is based on DOE G 413.3-19, Staffing Guide for Project Management.
• Spreadsheet is protected without a password. To unprotect, go to <Tools> <Protection> <Unprotect Sheet>.
• Project characteristic factors are listed at the end of this spreadsheet, and its values can be modified. If modified, please document accordingly.
• Spreadsheet is protected for entry only in the yellow highlighted cells.
• For project characteristics except PV and PF, please select from the cell's pull down list.

## factors
FACTORS
CT | value
Cost-reimbursement | 0.1
Fixed-price (firm, no incentive) | 0
Fixed-price (price adjustments, no incentive) | 0
Incentive (cost-reimbursement) | 0.1
Incentive (fixed-price) | 0
Indefinite-delivery | 0.2
T&M | 0.2
EI | value
High | 0.1
Low | 0
Medium | 0.05
HC
HC1
HC2
HC3
none
TR
High
Medium
Low
IR
A
B
C
D
NP
PP
PCmatrix1 | A | B | C | D | NP | PP
High | High | High | High | Medium | Medium | Medium
Medium | High | High | Medium | Low | Low | Low
Low | Medium | Medium | Low | Low | Low | Low
PCmatrix2 | HC1 | HC2 | HC3 | none
High | High | High | High | Medium
Medium | High | High | Medium | Low
Low | Medium | Medium | Low | Low
PC | value
High | 0.2
Low | 0
Medium | 0.1
PE | value
DOE Direct | 0.5
DOE M&O | 0.2
DOE M&O (non-profit) | 0.1
DOE M&O (non-profit)/sub | 0
DOE M&O/sub | 0
PP | value
CD-0 | 2
CD-1 | 1.1
CD-2 | 0.5
CD-3 | 0
PT | value
construction | 0.025
D&D | 0.05
ER | 0.075
MIE | 0
PU | value
No | 0
Yes | 0.1
RI | value
High | 0.1
Low | 0
Medium | 0.05
FAPs
PT | Construction | D&D | ER | MIE | Construction | D&D | ER | MIE | Construction | D&D | ER | MIE | Construction | D&D | ER | MIE
PP | CD-0 | CD-0 | CD-0 | CD-0 | CD-1 | CD-1 | CD-1 | CD-1 | CD-2 | CD-2 | CD-2 | CD-2 | CD-3 | CD-3 | CD-3 | CD-3
contracting, subcontracting, and property management | 15% | 30% | 30% | 25% | 5% | 15% | 15% | 15% | 5% | 15% | 15% | 25% | 20% | 20% | 20% | 8%
program and project planning, control and management | 25% | 15% | 15% | 30% | 20% | 30% | 30% | 38% | 20% | 30% | 30% | 35% | 20% | 20% | 20% | 35%
science, engineering, and design support | 25% | 20% | 20% | 15% | 40% | 20% | 20% | 15% | 25% | 15% | 15% | 17% | 20% | 10% | 7% | 15%
construction oversight and management | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5%
quality assurance | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 9% | 6% | 7% | 5% | 5% | 5% | 5% | 5%
environment, safety, and health | 20% | 10% | 10% | 3% | 20% | 15% | 15% | 5% | 20% | 15% | 15% | 5% | 10% | 20% | 20% | 15%
finance and administration | 5% | 15% | 15% | 22% | 5% | 12% | 12% | 20% | 5% | 8% | 5% | 10% | 5% | 8% | 8% | 10%
safeguards and security | 5% | 5% | 5% | 0% | 5% | 5% | 3% | 2% | 5% | 5% | 3% | 3% | 4% | 5% | 5% | 3%
operations oversight | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 5% | 5% | 0% | 10% | 5% | 5% | 4%
public affairs and stakeholder relations | 5% | 5% | 5% | 5% | 5% | 3% | 5% | 5% | 1% | 1% | 5% | 0% | 1% | 2% | 5% | 0%
Note on A3: ref.: FAR Parts 16 and 17.6.
Note on A17: ref.: DOE-STD-1027-92, Attachment 1.
Note on A28: ref.: DOE O 470.4B Chg 2, Appendix B, Section 1, Chapter II.

## acronyms
ACRONYMS
Chg | change
CT | contract type
D&D | decontaminationand decommissioning
DOE | U.S. Department of Energy
EI | external influence
ER | environmental remediation
FAP | functional area percentages
FAR | Federal acquisition regulation
FTE | full time equivalent
HC | hazard category
IR | importance rating
MIE | major item of equipemnt
O | order
PC | project complexity
PE | project execution
PF | productivity factor
PP | project phase
PS | project staffing
PT | project type
PU | project uniqueness
PV | project value
RI | regulatory involvement
RS | PS for associated functional area
STD | standard
TR | technology readiness

## version
VERSION
date | version | description
2017-04-12 | 11 | • Sheet "main": Added version field. • Sheet "verison": New sheet. • Importance rating (IR): Ref. to DOE O 470.4B Chg 1 updated to Chg 2 including hlink.