## Slide 1: ALIGNING CONTRACT INCENTIVES
John Longenecker (EFCOG Managing Director), Moderator
Norm Sandlin (B&W)
Bill Shingler (Fluor)
Susan Stiger (EFCOG Vice Chair, Bechtel)
James Krupnick, LBNL Ellen Livingston-Behan, URS
Rob Nagel, CH2M Hill Frank Sheppard, Parsons
Ed Rogers, Bechtel Cathy Snyder, Lockheed-Martin
Roy Schepens, EFCOG Director, Parsons
Notes: 1
Clay attending DOE PM Workshop today.

## Slide 2: Charter & Objectives
EFCOG was chartered by DOE to identify best practices, evaluate lessons learned, develop model approaches to:
Improve the effectiveness of incentives for capital asset and other major DOE projects with tangible deliverables
Support alignment of government and contractor interests and ensure the parties appropriately bear the benefits and accountability for their respective actions and performance
Ensure that incentives are linked to and effectively support project outcomes
Ensure that incentives earned are consistent with contractor performance

## Slide 3: EFCOG Observations
Contract incentives alone do not yield successful projects.
  Consensus on a clear value proposition for project completion
  Thoughtful definition and agreement on project scope
  Realistic assessment of risk/uncertainty, with effective management strategies
  Commitment to lifecycle funding
Challenging but achievable incentives to complete projects on time, on cost, with desired operability are best for all
Missions, contracts and projects are varied; one incentive approach will not be effective for all

## Slide 4: EFCOG Observations cont.
A number of factors, including incentives, motivate contractors.
Even well-intentioned incentive structures can have unintended consequences.
Complemented by DOE’s Management Reform and CPMI actions:
  Enhanced implementation of peer reviews
  Line management accountability for project funding and priority
  Rules of Thumb to clarify roles, responsibilities and expectations
  Comprehensive project team accountability for project success
  Federal and contractor project leadership qualifications and experience

## Slide 5
Key Principles & Lessons Learned
Incentives
Alignment
Common Knowledge, Objectives
Flexibility
Discipline, Partnership, Fair Play
Smart Balance
Objectivity
Selective, Realistic
Authority,
Accountability

## Slide 6: Gain Share/Pain Share Incentive Approaches
Effective if applied appropriately, consistent with project management structure, risk profile, authorities/accountabilities. Ineffective if key factors are not aligned or critical elements are outside DOE or contractor control.
Best Practices/Recommendations
Limit application to key performance objectives
Phase incentives on major capital projects – shift appropriate risk to contractor when project is sufficiently definitized and mature
Ensure incentives are balanced and reflect contractor’s authority to achieve desired results
Consider appropriate limits to both gain and pain

## Slide 7: Gain Share/Pain Share cont.
Provisional Fee
Earned for results of true value to DOE
Ability to earn progress fee is important on lengthy projects
Can help balance focus on interim objectives and the ultimate goal. An earned/provisional mix is most effective.
Requirements for Effective Cost Ceiling/Fixed Price Approaches
Scope is well defined, including requirements
Mutual agreement on TPC; total project funding profile is assured
Contractor controls project execution and risk resolution
Interfaces are few and well understood/controlled
Technology is well-established and proven
Effective change control is in place, functioning, and timely

## Slide 8: Major First-of-a-Kind Nuclear Project
Major performance elements – safety, quality, schedule, cost, and functionality
    Very difficult to optimize all elements at the same time
    Safety and quality factors should outweigh the cost factor
    Difficult to reach consensus on what constitutes sufficient safety when cost is also considered
It is virtually impossible to establish one universal performance incentive structure at the beginning of longer-term projects
A tendency to drive down cost targets early in the CD process can lead to misalignment
Review key assumptions in discussions with stakeholders

## Slide 9: Major First-of-a-Kind Nuclear Project
Phase | Uncertainty | Risk Level | Recommended Incentive
Preliminary Design | TRL, design requirements | High | CPFF
Final Design | TRL, design requirements | Mod-High | CPFF or CPAF
Construction | Design changes, SOT, ISOT | Mod | CPAF/CPIF (schedule, cost)
Start-up | Training, ORR, NTP | Mod | CPAF/CPIF (cost, schedule)
Operations | Feedstock, throughput, maintenance | Low- Mod | CPIF (productivity, cost)

## Slide 10: 7 Steps to Alignment With Project Objectives
Identify what is known, and what is not known
Evaluate what is known, and what is not known, about variables that may affect desired project outcomes
Perform comprehensive risk analysis
Assign risk to the appropriate party with clear alignment to defined responsibilities and authorities
Align contract with the project characteristics and risk profile
Select incentive structure appropriate to the risk, responsibilities and authorities
Select specific incentives and/or disincentives most likely to motivate the type of performance desired.

## Slide 11: Misalignment A Root Cause Analysis
Scope, schedule, cost and other variables are not well definitized...
Contract awarded with expectation that post-award baseline “true-up” process will satisfactorily address risks…
Incentives are established using true-up baseline, sometimes without resolution of all contractual issues at that point…
As more project definitization occurs, incentives can become increasingly misaligned with desired outcome…
Rebaselining can occur due to directed changes, unidentified or underestimated risks realized, funding issues. The entire project is reset, typically with increased EAC and schedule extension.
Root cause: insufficient project definitization and risk analysis prior to establishing incentives and commencing work.

## Slide 12: Models for Improved Alignment
Based on 7-Step Process:
When project uncertainties materially affect DOE’s ability to define scope, schedule, estimated cost and performance risk...
  Existing Contracts: identify and implement actions for improvement
  New Awards: Consider alternate Solicitation and Contract models to confirm definition of scope/schedule/cost and performance requirements; establish aligned incentives
    Solicitation Model for potential high-risk capital projects with longer periods of performance, technological and other risks
    Contract Model for post-award project definition and incentives with phased approach to project completion

## Slide 13: Closing Thoughts
  Achieving project goals and earning maximum fee against challenging, achievable objectives is the optimum outcome for both parties.
  Integrate project and contract personnel into an effective partnership early.
Well-aligned incentives are valuable but will not single-handedly drive a project to a successful conclusion.
  Align with strategies to address issues that can more directly influence major project progress (funding profile, scope definition/redefinition, cost control, change management, misalignment in objectives, etc.
Consider a phased approach to project incentives, aligned with project maturity.
Emphasize graded approach to project requirements and value engineering to support life-cycle improvements of benefit to DOE.

## Slide 14: Closing Thoughts
  Achieving project goals and earning maximum fee against challenging, achievable objectives is the optimum outcome for both parties.
  Integrate project and contract personnel into an effective partnership early.
Well-aligned incentives are valuable but will not single-handedly drive a project to a successful conclusion.
  Align with strategies to address issues that can more directly influence major project progress (funding profile, scope definition/redefinition, cost control, change management, misalignment in objectives, etc.
Consider a phased approach to project incentives, aligned with project maturity.
Emphasize graded approach to project requirements and value engineering to support life-cycle improvements of benefit to DOE.

## Slide 15: Questions
  Do you think DOE does a good job with contract incentives? Can you give examples of both good and not-so-good application of contract incentives by DOE.

## Slide 16: Questions
  Given that we know the FAR limits the maximum amount of fee on cost reimbursable contracts, and we know there is no limit on profit potential for firm-fixed price contracts. Since profit drives business and our economy, isn’t fixed price contracts the way to go?

## Slide 17: Questions
  What is more important to our contractors…making more money on project-specific incentives or maintaining the company’s reputation to better position itself for the potential for future work?

## Slide 18: Questions
  Do you support converting cost reimbursable contracts to fixed price when the design has matured?

## Slide 19: Questions
  How do contractors react when the contract incentives are not perfectly aligned?

## Slide 20: Questions
  Can a contractor with little or no experience managing firm fixed price projects reasonably be expected to accept the additional risk associated with firm fixed price contracting?

## Slide 21: Questions
  From a contractor’s perspective, are internal fee pressures any different in a privately held firm than in one that is publicly held?

## Slide 22: Questions
  Earning the maximum fee on a contract may require that a contractor reduce payroll costs through layoffs. At the same time, employees are typically your primary assets, and contractors are often reluctant to let people go unless forced to by external budgetary pressures. Are your companies prepared to self-manage your payroll costs without external pressures in order to optimize the fee you can earn on a contract?

## Slide 23: Questions
  Are first-of-a-kind nuclear projects not candidates for Firm Fixed Price contracting? Why, why not?

## Slide 24: Questions
  Can good incentive approaches overcome ineffective application of project management principles, resulting in successful project outcomes?

## Slide 25: Questions
  How critical are incentives to the success of a major capital project? Examples?

## Slide 26: Questions
  What are the most critical elements of an effective incentive approach?

## Slide 27: Questions
  When are true cost ceilings (a fixed price approach) appropriate on major projects? What pre-requisites are most important for such an approach to be effective?